## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | RAYAPUREDDY NITHIN | 2025-12-11 | Visa application dataset contained missing values and inconsistent formats | Sprint 1 | Backend Team | Data Preprocessing | Cleaned dataset, handled missing values, standardized formats | 2025-12-06 | Closed | Dataset validated successfully
2 | RAYAPUREDDY NITHIN | 2025-12-11 | Processing time not calculated correctly for some applications | Sprint 1 | Backend Team | Logic | Fixed date parsing and recalculated processing_time_days | 2025-12-09 | Closed | Target variable generated correctly
3 | RAYAPUREDDY NITHIN | 2025-12-25 | Seasonal trend not reflected in EDA visualizations | Sprint 2 | Backend Team | Analysis | Added month-wise and seasonal feature engineering | 2025-12-15 | Closed | Seasonal patterns identified
4 | RAYAPUREDDY NITHIN | 2026-01-08 | Regression model producing high error initially | Sprint 3 | AI / ML Team | Model Training | Tuned hyperparameters and selected best-performing model | 2026-01-03 | Closed | MAE and RMSE improved
5 | RAYAPUREDDY NITHIN | 2026-01-22 | Predicted processing time not displaying on web interface | Sprint 4 | Frontend + Backend | Integration | Connected ML prediction engine with UI | 2026-01-06 | Closed | Output displayed correctly
6 | RAYAPUREDDY NITHIN | 2026-01-22 | User input validation missing in visa details form | Sprint 4 | Frontend + Backend | UI/Validation | Added input validation and error messages | 2026-01-10 | Closed | User-friendly form
7 | RAYAPUREDDY NITHIN | 2026-01-22 | Backend API returning delayed responses | Sprint 4 | Frontend + Backend | Performance | Optimized API and caching logic | 2026-01-15 | Closed | Response time reduced
8 | RAYAPUREDDY NITHIN | 2026-01-22 | Prediction results not updating dynamically on dashboard | Sprint 4 | Frontend + Backend | Integration | Fixed data binding and refresh logic | 2026-01-20 | Closed | Dashboard working properly
9 | RAYAPUREDDY NITHIN | 2026-01-22 | Cloud deployment configuration issue | Sprint 4 | Frontend + Backend | Deployment | Updated deployment settings and environment variables | 2026-01-21 | Closed | Application deployed successfully
10 | RAYAPUREDDY NITHIN | 2026-01-22 | Minor UI alignment and label issues in estimator page | Sprint 4 | Frontend + Backend | UI | Corrected layout and labels | 2026-01-22 | Closed | Presentation-ready